## Slide 1
DISCUSSION DOCUMENT
VAT refund at Hanoi City Tax
Scenario model and next actions following the Department of Taxation’s guidance letter
September 2026

## Slide 2
The refund file is on hold pending the Department of Taxation’s guidance
The parties have not yet agreed on how the relevant regulation should be interpreted.
Guidance requested
Hanoi City Tax and the client each sent an official letter to the Department of Taxation (DoT) asking for guidance.
WE ARE HERE
DoT reviewing internally
The DoT is processing the request and preparing a guidance letter.
DoT issues guidance
The trigger point for the scenario model in this document.
Hanoi City Tax decides
Based on the guidance, Hanoi City Tax either approves or rejects the refund.
Why plan now: once the guidance is issued, Hanoi City Tax may act quickly. Agreeing the response to each scenario in advance lets the client react within days instead of weeks.
VAT refund at Hanoi City Tax | Scenario model | Discussion document
2

## Slide 3
Three escalation steps, each with a clear exit if the outcome is favourable
End-to-end view of the scenario model
TRIGGER
DoT issues guidance letter
Obtain the letter on issuance and align on its interpretation with the client.
1
STEP 1
Leadership-level discussion with Hanoi City Tax
Informal meeting to learn Hanoi City Tax’s position before any minutes or decision are issued.
EXIT IF
Refund approved, or client accepts carry-forward
ESCALATE IF
Refund rejected, or carry-forward only and client still wants a refund
2
STEP 2
Formal letter to Hanoi City Tax
Copy to the DoT. Request the refund, propose a joint meeting, and state the intention to escalate.
EXIT IF
Hanoi City Tax approves, or joint meeting agrees on refund
ESCALATE IF
Rejection maintained, or unilateral inspection minutes
3
STEP 3
Petition to the Ministry of Finance
Address to MoF leadership; copy DoT, Hanoi City Tax, the Embassy and JCCI.
EXIT IF
Tax authorities’ unified position approves the refund
ESCALATE IF
Unified position rejects the refund
FINAL
Client decides on further recourse
Administrative complaint (low chance of success) or administrative lawsuit.
VAT refund at Hanoi City Tax | Scenario model | Discussion document
3

## Slide 4
Step 1: an early, informal discussion reveals which of three scenarios applies
Held at leadership level so the position we hear is reliable. No written submission is needed yet.
STEP 1
Discussion with Hanoi City Tax
Leadership level, informal
SCENARIO 1
Refund approved
Guidance is clear to Hanoi City Tax
FAVOURABLE
SCENARIO 2
No refund; carry-forward allowed
Amount credited against future tax periods
INTERMEDIATE
SCENARIO 3
Refund rejected
No refund and no carry-forward
ADVERSE
OUTCOME
Refund processed; case closed
SCENARIO 2.1
Client accepts carry-forward; case closed
SCENARIO 2.2
Client still requests a refund; treated as Scenario 3
NEXT
Go to Step 2: formal letter
CLIENT DECISION
Is carry-forward acceptable?
Under Scenario 2 the amount is not refunded in cash. It is offset against future tax payable, and it is not known how long full utilisation would take.
Agreeing this in advance decides whether the file stops at 2.1 or moves on to Step 2.
Client action
Favourable outcome
Intermediate outcome
Adverse outcome
VAT refund at Hanoi City Tax | Scenario model | Discussion document
4

## Slide 5
Step 2: a formal letter creates a written record before Hanoi City Tax acts
Triggered by Scenario 3 or Scenario 2.2. Hanoi City Tax may respond in one of four ways.
STEP 2
Formal letter to Hanoi City Tax
Copy to the DoT.
Consider copying the MoF, the Embassy and JCCI.
Content: see next slide.
RESPONSE A
Hanoi City Tax approves the refund
FAVOURABLE
RESPONSE B
Joint meeting of the parties
Hanoi City Tax reports to the DoT, which chairs
INTERMEDIATE
RESPONSE C
Unilateral inspection minutes
Hanoi City Tax is entitled to do this
ADVERSE
RESPONSE D
Rejection maintained
In a written reply, or no response
ADVERSE
OUTCOME
Refund processed; case closed
OUTCOME
Agreement leads to a refund. If still adverse, go to Step 3
CLIENT RESPONSE
Record disagreement in the minutes; ask for the file to be held pending MoF guidance
CLIENT RESPONSE
Use the written position as the basis for escalation
STEP 3
Petition to the Ministry of Finance
Client action
Favourable outcome
Intermediate outcome
Adverse outcome
VAT refund at Hanoi City Tax | Scenario model | Discussion document
5

## Slide 6
Step 3: escalation to the Ministry of Finance leads to a final, unified position
Sent directly to MoF leadership, not back to the DoT, and only once Hanoi City Tax has acted or responded in writing.
STEP 3
Petition to the Ministry of Finance
To MoF leadership; copy DoT, Hanoi City Tax, the Embassy and JCCI
MOF RESPONSE
Directs the DoT to convene an inter-agency meeting
MOST LIKELY
MOF RESPONSE
Replies directly in writing
CONTINGENCY
MoF refers the file back to the DoT or Hanoi City Tax
The client returns to discussions with Hanoi City Tax
RESULT
Final unified position of the tax authorities
MoF, DoT and Hanoi City Tax
APPROVED
Refund processed
REJECTED
Client considers further recourse
Administrative complaint: low chance of success, as the MoF and DoT have already aligned.
Administrative lawsuit before the court.
The decision rests with the client.
Client action
Favourable outcome
Intermediate outcome
Adverse outcome
VAT refund at Hanoi City Tax | Scenario model | Discussion document
6

## Slide 7
The Step 2 letter makes three points and signals the escalation path
TO
Hanoi City Tax
COPY
Department of Taxation, the authority that issued the guidance
CONSIDER COPYING
Ministry of Finance, the Embassy, JCCI
TIMING
Immediately after Step 1, if Hanoi City Tax’s position is unfavourable
1
Request the refund
The client reads the DoT’s guidance as confirming eligibility for the refund, and asks Hanoi City Tax to process it.
2
Propose a joint meeting if the guidance is unclear
If Hanoi City Tax considers the guidance insufficiently clear, it is asked to report to the DoT and arrange a meeting of the parties (with the MoF, the Embassy and JCCI where appropriate) to reach a unified view.
3
State the intention to escalate
If Hanoi City Tax still does not agree, the client will petition the Ministry of Finance and copy the relevant parties.
VAT refund at Hanoi City Tax | Scenario model | Discussion document
7

## Slide 8
Summary of scenarios and client actions
Scenario | Hanoi City Tax position | Client action | Outcome
1 | Approves the refund in line with the DoT guidance | Complete the refund formalities | Refund
2.1 | No refund; carry-forward allowed | Accept carry-forward and close the file | Carry-forward; closed
2.2 | No refund; carry-forward allowed | Still request a refund (utilisation period uncertain); treat as Scenario 3 | Go to Step 2
3 | Rejects the refund | Step 2 formal letter; if still adverse, Step 3 petition to the MoF | Per final position
3, minutes | Issues inspection minutes unilaterally | Record disagreement; request the file be held pending MoF guidance | Go to Step 3
Final | Unified position rejects the refund | Client considers an administrative complaint or lawsuit | Client decision
VAT refund at Hanoi City Tax | Scenario model | Discussion document
8

## Slide 9
Four principles guide how we manage the case
Learn the position early
Meet Hanoi City Tax at leadership level as soon as the guidance is issued. Waiting for minutes or a decision leaves too little time to respond.
Escalate in sequence
Petition the MoF only after Hanoi City Tax has acted or replied in writing. Escalating earlier risks the MoF referring the file back, since the DoT has already given guidance.
Keep a written record
The Step 2 letter is the basis for the client’s comments in any minutes and for escalation if Hanoi City Tax acts unilaterally.
Manage what we can control
Hanoi City Tax is entitled to issue minutes and decisions unilaterally. The client cannot prevent this, but can manage the situation at every step.
VAT refund at Hanoi City Tax | Scenario model | Discussion document
9

## Slide 10
Next actions and decisions needed from the client
Our team
Monitor the DoT’s guidance and obtain a copy as soon as it is issued
Analyse the guidance and prepare the client’s arguments for Step 1
Arrange the leadership-level meeting with Hanoi City Tax
Pre-draft the Step 2 letter so it can be sent immediately if needed
Compile all correspondence to date for a possible MoF petition
Client decisions
Whether carry-forward (Scenario 2) is an acceptable outcome
Whether to copy the MoF, the Embassy and JCCI on the Step 2 letter
Appetite for an administrative complaint or lawsuit if the final position is adverse
VAT refund at Hanoi City Tax | Scenario model | Discussion document
10